## Sheet1
Project Management - Project Task Planning List
# | Project | Process | Task Name | UOM | Road | Quantity | Actual | Resource Type | Resource Name | No of Objects | Per day output | Total Days | P Start Date | P End Date | Planning Id | Edit
1 | ANAGHA | RECEIVED APPROVAL PLAN | APPROVAL PLAN RECEIVED AND UPLOADED | NO'S | No Roads | 2 | 0 | CW | CW - 1 | 1 | 1 | 2 | 23/04/2018 | 24/04/2018 | 7803 | ***
2 | ANAGHA | SCOPE OF WORK FINALIZATION | SCOPE OF WORK FINALIZATION BY KNS MANAGEMENT | NO'S | No Roads | 1 | 1 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7804 | ***
3 | ANAGHA | CONSULTANT IDENTIFICATION | PRINCIPLE-CONSULTANT | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7805 | ***
4 | ANAGHA | CONSULTANT IDENTIFICATION | ELECTRICAL CONSULTANT | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7806 | ***
5 | ANAGHA | CONSULTANT IDENTIFICATION | LAND SCAPE CONSULTANT | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7807 | ***
6 | ANAGHA | CONSULTANT IDENTIFICATION | PHE CONSULTANT | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7808 | ***
7 | ANAGHA | PRELIMINARY SKETCHES | ENTRANCE ARCH SKETCH | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7809 | ***
8 | ANAGHA | PRELIMINARY SKETCHES | COMPOUND WALL SKETCH | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7810 | ***
9 | ANAGHA | PRELIMINARY SKETCHES | PARK AMENITIES SKETCH | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7811 | ***
10 | ANAGHA | PRELIMINARY SKETCHES | CLUB HOUSE SKETCH | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7812 | ***
11 | ANAGHA | DRAWING GOOD FOR CONSTRUCTION | ALL DRAWINGS RECEIVED AND UPLOADED | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7813 | ***
12 | ANAGHA | KICK OFF MEETING | KICK OFF MEETING MOM UPDATION | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7814 | ***
13 | ANAGHA | BOREWELL | PLACE IDENTIFICATION | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7815 | ***
14 | ANAGHA | BOREWELL | DIGGING | RMT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7816 | ***
15 | ANAGHA | BOREWELL | PIPE INSTALLATION | RMT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7817 | ***
16 | ANAGHA | BOREWELL | PUMPS INSTALLATION & COMMISSIONING | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7818 | ***
17 | ANAGHA | COMPOUND WALL (PRECAST) | PRECAST COMPOUND WALL | RMT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7819 | ***
18 | ANAGHA | PARK DEVELOPMENT | CHAIN LINK FENCING FABRICATION WORK | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7820 | ***
19 | ANAGHA | PARK DEVELOPMENT | DRIP IRRIGATION PLUMBING WORK | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7825 | ***
20 | ANAGHA | PARK DEVELOPMENT | PATHWAY | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7824 | ***
21 | ANAGHA | PARK DEVELOPMENT | GRASS DOUBLING | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7823 | ***
22 | ANAGHA | PARK DEVELOPMENT | TREE PLANTATION | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7822 | ***
23 | ANAGHA | PARK DEVELOPMENT | CHILDERNS PLAY AREA | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7821 | ***
24 | ANAGHA | PARK DEVELOPMENT | JOGGING TRACK | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7826 | ***
25 | ANAGHA | ENTRANCE ARCH | EARTHWORK EXCAVATION | CUM | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7827 | ***
26 | ANAGHA | ENTRANCE ARCH | BLASTING/STONE BREAKING WORK | RFT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7828 | ***
27 | ANAGHA | ENTRANCE ARCH | PLAIN CEMENT CONCRETE (PCC) | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7829 | ***
28 | ANAGHA | ENTRANCE ARCH | SIZE STONE MASSONARY | CUM | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7831 | ***
29 | ANAGHA | ENTRANCE ARCH | FOOTING | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7830 | ***
30 | ANAGHA | ENTRANCE ARCH | CONSTRCTION OF COLUMN BELLOW PLINTH | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7832 | ***
31 | ANAGHA | ENTRANCE ARCH | PLINTH BEAM CONSTRUCTION | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7833 | ***
32 | ANAGHA | ENTRANCE ARCH | DPC | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7834 | ***
33 | ANAGHA | ENTRANCE ARCH | BLOCK WORK | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7835 | ***
34 | ANAGHA | ENTRANCE ARCH | LINTELS | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7836 | ***
35 | ANAGHA | ENTRANCE ARCH | SLAB/PARGOLA CONSTRUCTIONS | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7837 | ***
36 | ANAGHA | ENTRANCE ARCH | CONSTRUCTION OF SECURITY CABIN | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7838 | ***
37 | ANAGHA | ENTRANCE ARCH | PLUMBING WORK | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7839 | ***
38 | ANAGHA | ENTRANCE ARCH | ELECTRICAL WORK | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7840 | ***
39 | ANAGHA | ENTRANCE ARCH | PLASTRING | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7841 | ***
40 | ANAGHA | ENTRANCE ARCH | FLOORING | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7842 | ***
41 | ANAGHA | ENTRANCE ARCH | DOORS & WINDOW FIXING | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7843 | ***
42 | ANAGHA | ENTRANCE ARCH | ENTRANCE ARCH PAINTING | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7844 | ***
43 | ANAGHA | ENTRANCE ARCH | PLUMBING FITTINGS FIXING | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7845 | ***
44 | ANAGHA | ENTRANCE ARCH | ELECTRICAL FIXTURES FIXING | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7846 | ***
45 | ANAGHA | OVERHEAD TANK | EARTHWORK EXCAVATION | CUM | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7847 | ***
46 | ANAGHA | OVERHEAD TANK | BLASTING/STONE BREAKING WORK | RFT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7848 | ***
47 | ANAGHA | OVERHEAD TANK | PLAIN CEMENT CONCRETE (PCC) | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7849 | ***
48 | ANAGHA | OVERHEAD TANK | COMPLETION OF FOOTING & RAFT BEAM | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7850 | ***
49 | ANAGHA | OVERHEAD TANK | COMPLETION OF COLUMN | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7851 | ***
50 | ANAGHA | OVERHEAD TANK | COMPLETION OF BOTTOM SLAB AND BEAM | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7852 | ***
51 | ANAGHA | OVERHEAD TANK | COMPLETION OF RCC WALL CONSTRUCTION | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7853 | ***
52 | ANAGHA | OVERHEAD TANK | COMPLETION OF DOME CONSTRUCTION | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7854 | ***
53 | ANAGHA | OVERHEAD TANK | TANK INSIDE WATERPROOFING | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7856 | ***
54 | ANAGHA | OVERHEAD TANK | CHAMBER CONSTRUCTION FOR GATEVALVES | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7858 | ***
55 | ANAGHA | OVERHEAD TANK | COMPLETION OF INSIDE & OUTSIDE PLASTERING | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7855 | ***
56 | ANAGHA | OVERHEAD TANK | OHT PAINTING WORK | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7857 | ***
57 | ANAGHA | OVERHEAD TANK | LADDER FABRICATION & FIXING | KG | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7860 | ***
58 | ANAGHA | OVERHEAD TANK | CI PIPE & GATE VALVE FIXING FOR INLET & DELIVERY | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7859 | ***
59 | ANAGHA | OVERHEAD TANK | TANK LOADING & LEAKAGE TESTING | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7861 | ***
60 | ANAGHA | SEWAGE TREATMENT PLANT | EARTHWORK EXCAVATION | CUM | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7862 | ***
61 | ANAGHA | SEWAGE TREATMENT PLANT | BLASTING/STONE BREAKING WORK | RFT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7863 | ***
62 | ANAGHA | SEWAGE TREATMENT PLANT | PLAIN CEMENT CONCRETE (PCC) | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7864 | ***
63 | ANAGHA | SEWAGE TREATMENT PLANT | RCC WALL CONSTRUCTION WORK | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7865 | ***
64 | ANAGHA | SEWAGE TREATMENT PLANT | PLANT ROOM CONSTRUCTION | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7866 | ***
65 | ANAGHA | SEWAGE TREATMENT PLANT | CONSTRUCTION OF SLUDGE DRYING BED | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7867 | ***
66 | ANAGHA | SEWAGE TREATMENT PLANT | CONSTRUCTION OF SETTLING TANK | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7868 | ***
67 | ANAGHA | SEWAGE TREATMENT PLANT | STP PAINTING WORK | SQ.MT | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7869 | ***
68 | ANAGHA | SEWAGE TREATMENT PLANT | PUMPS INSTALLATION & COMMISSIONING | MLS | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7870 | ***
69 | ANAGHA | BESCOM APPROVALS | APPROVED DOCUMENTS COLLECTION (IN-HOUSE) | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7871 | ***
70 | ANAGHA | BESCOM APPROVALS | POWER ESTIMATION / DRAWING AND DOCUMENTS(EXTERNAL) | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7872 | ***
71 | ANAGHA | BESCOM APPROVALS | FILE SUBMISSION TO DEPARTMENT | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7873 | ***
72 | ANAGHA | BESCOM APPROVALS | SUBMISSION OF ELECTRICAL MATERIALS PURCHASE BILLS TO DEPARTMENT | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7874 | ***
73 | ANAGHA | BESCOM APPROVALS | DEPARTMENT APPROVALS FEE (DEMAND DRAFT) | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7875 | ***
74 | ANAGHA | BESCOM APPROVALS | DEPARTMENT INSPECTION AT LAYOUT | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7876 | ***
75 | ANAGHA | BESCOM APPROVALS | ELECTRICITY APPROVALS | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7877 | ***
76 | ANAGHA | BESCOM APPROVALS | LAYOUT CHARGING | NO'S | No Roads | 0 | 0 |  |  | 0 | 0 | 0 | 00/00/0000 | 00/00/0000 | 7878 | ***
77 | ANAGHA | MAINTENANCE | REPLANTING | NO'S | No Roads | 100 | 20 | CW | CW - 1 | 1 | 1 | 97 | 12/04/2018 | 02/08/2018 | 7889 | ***
78 | ANAGHA | MAINTENANCE | SOIL DIGGING | NO'S | No Roads | 100 | 32 | CW | CW - 1 | 1 | 1 | 97 | 03/08/2018 | 23/11/2018 | 7887 | ***
79 | ANAGHA | MAINTENANCE | ROOT TRIMMING | NO'S | No Roads | 1001 | 118 | CW | CW - 1 | 1 | 1 | 981 | 24/11/2018 | 11/01/2022 | 7886 | ***
80 | ANAGHA | MAINTENANCE | DE-WEEDING | NO'S | No Roads | 2000 | 154.01 | CW | CW - 1 | 10 | 1 | 196 | 18/03/2019 | 31/10/2019 | 7885 | ***
81 | ANAGHA | MAINTENANCE | PRUNING - TRIMMING | NO'S | No Roads | 100 | 9 | CW | CW - 1 | 1 | 1 | 97 | 09/07/2019 | 29/10/2019 | 7884 | ***
82 | ANAGHA | MAINTENANCE | LAWN MOWING | NO'S | No Roads | 100 | 6 | CW | CW - 1 | 1 | 1 | 97 | 30/10/2019 | 19/02/2020 | 7883 | ***
83 | ANAGHA | MAINTENANCE | EDGES TRIMMING | NO'S | No Roads | 100 | 11 | CW | CW - 1 | 1 | 1 | 97 | 20/02/2020 | 11/06/2020 | 7882 | ***
84 | ANAGHA | MAINTENANCE | PESTICIDE APPLY | NO'S | No Roads | 100 | 6 | CW | CW - 1 | 1 | 1 | 97 | 12/06/2020 | 02/10/2020 | 7881 | ***
85 | ANAGHA | MAINTENANCE | FERTILIZER APPLYING | NO'S | No Roads | 100 | 5 | CW | CW - 1 | 1 | 1 | 96 | 03/10/2020 | 23/01/2021 | 7880 | ***
86 | ANAGHA | MAINTENANCE | SHEEP MANURE APPLYING | NO'S | No Roads | 100 | 7 | CW | CW - 1 | 1 | 1 | 97 | 25/01/2021 | 17/05/2021 | 7888 | ***
87 | ANAGHA | MAINTENANCE | WATERING | NO'S | No Roads | 1000 | 65.26 | CW | CW - 1 | 91 | 1 | 11 | 18/05/2021 | 29/05/2021 | 7879 | ***
88 | ANAGHA | MAINTENANCE | OLD PROJECTS CLOSE | MLS | No Roads | 10 | 0 | CW | CW - 10 | 1 | 10 | 1 | 12/07/2018 | 12/07/2018 | 19023 | ***
89 | ANAGHA | MAINTENANCE | SITE-CLEANING | MLS | No Roads | 200 | 142 | CW | CW - 1 | 0 | 1 | 314 | 11/09/2018 | 11/09/2019 | 20353 | ***